## Features
DONE | ID | Description | Priority | Difficulty | Req. | Assigned | Notes
1 | 1 | Implement the best score stat at the top of the game screen | HIGH | MEDIUM |  | Michael
1 | 2 | Make stats at top of screen fit properly | HIGH | EASY |  | Sam
1 | 3 | Adjust variables (e.g. timer acceleration, map file), to make the difficulty more appropriate | HIGH | EASY |  | Joe
1 | 4 | 'Turn off' landscape game view | HIGH | MEDIUM |  | Nick
1 | 5 | Remove the tiny gap between the map and the timer | LOW | EASY |  | Sam
1 | 6 | Better mechanics for updating the board | MEDIUM | MEDIUM |  | Sam | faster?
1 | 7 | Fix game resuming after in-game help | HIGH | HARD |  | Vanita
| 1 | Complete user registration/login | MEDIUM | MEDIUM |  | Michael
1 | 9 | Fix all warnings in Board class | LOW | EASY |  | Joe
1 | 10 | Implement a map | HIGH | HARD |  | Joe, Sam
1 | 11 | Timer 'slash' effect (as seen in Research and Other Notes\View\Gameplay.png) | MEDIUM | MEDIUM |  | Sam
1 | 12 | Create and implement a really good map | MEDIUM | MEDIUM | F.1 | Nick
1 | 13 | Change help activity to use images used for the game map | HIGH | MEDIUM | F.3.7 | Vanita | e.g. no help_screen_pads.png
1 | 14 | Make the imaginary path disappear when the user removes finger | MEDIUM | EASY |  | Sam
1 | 15 | Come up with a name | HIGH | EASY |  | Everyone | Drone Dispatch
1 | 16 | Create a logo | HIGH | MEDIUM |  | Nick
-1 | 17 | Sort high scores by score, time etc. |  | MEDIUM
1 | 18 | Create "delete scores" button in High Scores screen | MEDIUM | MEDIUM | F.3.4 | Michael
1 | 19 | End-of-game screen with high score name entry | HIGH | HARD | F.3.5 | Vanita
1 | 20 | "Various" help screens | HIGH | MEDIUM | F.3.7 | Vanita | From the requirements
1 | 21 | Add version to about screen | HIGH | EASY | F.3.6 | Joe
1 | 22 | Add more detailed credits to about screen | LOW | EASY | F.3.6 | Vanita | Add info on each team member
1 | 24 | End-of-game screen should notify user if they achieved a new high score | LOW | EASY | F.3.5 | Vanita | Included in design document.
1 | 25 | Rename "Scores" title with "Records" | MEDIUM | EASY | F.3.4 | Vanita | Same image as in main menu
-1 | 26 | Give drones shadows? |  | MEDIUM |  |  | A little OTT - there are other ways to improve graphics
1 | 29 | Do not allow user to choose CONTINUE if the last game ended | HIGH | HARD |  | Vanita
1 | 30 | Do not allow user to choose CONTINUE if no game is saved | HIGH | HARD | F.4 | Sam
1 | 31 | Make total time reflect accurately the time of the game | HIGH | MEDIUM |  | Sam
1 | 33 | Create and implement game sounds | HIGH | MEDIUM |  | Michael | From the "Sounds" list
1 | 34 | Tutorial | HIGH | HARD | F.3.7 | Vanita | Depends on research by Vanita on feature #20
1 | 35 | Non-circular drones | MEDIUM | HARD |  | Nick, Sam | For example planes or helicopters
1 | 36 | Settings screen | HIGH | MEDIUM | F.3.3 | Sam
1 | 37 | Prevent drones from travelling backwards at the end of their path | MEDIUM | MEDIUM |  | Sam
1 | 38 | Replace "Drone Game" or "TheDroneGame" with "Drone Dispatch" | HIGH | MEDIUM |  | Nick
1 | 39 | Properly format records screen | MEDIUM | MEDIUM |  | Michael
1 | 40 | Scale top-of-screen game stats correctly using images | LOW | MEDIUM |  | Nick
1 | 41 | Move "reset scores" from Records to Settings | MEDIUM | EASY |  | Sam
1 | 42 | Main Menu button in pause menu | LOW | MEDIUM |  | Joe
1 | 43 | Redesign enemy drones and position them correctly on screen | HIGH | MEDIUM |  | Nick
1 | 44 | Make crates appear larger when being carried by a drone | HIGH | MEDIUM |  | Nick
1 | 45 | Position timer and pause button correctly at bottom of screen | HIGH | EASY |  | Sam
-1 | 46 | "Restart" button in pause menu |  | MEDIUM
0 | 49 | Give drones a direction
0 | 50 | Remove landscape main menu
0 | 58 | Make paths 'curvy'
| 2 | Products MVC i.e. Paper Cutting -> Chinese, Japanes. | MEDIUM | MEDIUM |  |  | Build Products View where all Products such as Chinese, Japanese Paper Cutting.
1 | 3 | Build Artist MVC | MEDIUM | MEDIUM
| 4 | Ordering System i.e. Ordering Products i.e. Chinese Paper Cutting. | LOW
| 5 | Home page - Add and complete content for three headings | HIGH
| 6 | Gallery i.e. overal portfolio | MEDIUM
| 7 | Terms and Conditions / Privacy Policy | HIGH
| 8 | Resuming MVC Descriptions and Generating MVCs. | HIGH | MEDIUM
| 9 | Remove Type from Products for Chinese Paper Cutting. | HIGH
| 10 | Create Package Record i.e. “Chinese Paper Cutting” for Package “Paper Cutting”. | HIGH

## Sheet1
EASY | 1
MEDIUM | 2
HARD | 3
|  | Joe | 5
|  | Michael | 6
|  | Sam | 5

## Sounds
DONE? | ID | Sound | Description | Priority
| 1 | pick_up_crate | - | HIGH
| 2 | drop_crate | - | HIGH
| 3 | crash | - | HIGH
| 4 | timer_at_zero | - | HIGH
| 5 | new_game | - | LOW
| 6 | pause_game | - | MEDIUM
| 7 | continue_game | - | MEDIUM
| 8 | begin_path_draw | - | MEDIUM
| 9 | end_path_draw | - | MEDIUM
| 10 | in_game_new_best_score | Played as soon as the player beats the best score | LOW
| 11 | end_game_new_best_score | Used once the game has ended if the player set a new high score | LOW